## Task
ID | WBS | Task | Start | Successors | Finish | WBS predecessors | WBS successors | Duration | Predecessors | Progress | Hyperlink/File | Cost | Work | Remaining Cost | Early Start | Early Finish | Late Start | Late Finish | Early Slack | Critical Path | Notes | Baseline Start | Baseline Finish | Baseline Cost | ActualStart | ActualFinish | Outline Level | Late Slack | Actual Duration | Status | Priority | Resources
1 | 1 | Phase One - Software Deployment | 2026-01-01 |  | 2026-07-31 |  |  | 152Workday |  | 0% |  | £E. 0 | 3,016 Hour | £E.0 | 2026-01-01 | 2026-07-31 | 2026-01-01 | 2026-07-31 | 0 Workday | Yes |  |  |  | £E.0 | 2026-01-01 | 2026-05-04 | The task of 1 | 0 Workday | 87.9Workday | Not Started | None | 이영진; 최호승; 이재희; 이찬형
2 | 1.1 | 一、AI Model deployment | 2026-01-01 |  | 2026-07-31 |  |  | 152Workday |  | 0% |  | £E. 0 | 3,016 Hour | £E.0 | 2026-01-01 | 2026-07-31 | 2026-01-01 | 2026-07-31 | 0 Workday | Yes |  |  |  | £E.0 | 2026-01-01 | 2026-05-04 | The task of 2 | 0 Workday | 87.9Workday | Not Started | None | 이영진; 최호승; 이재희; 이찬형
3 | 1.1.1 | Stage 1. FPH detector 모델 검증 | 2026-02-27 |  | 2026-03-26 | 1.1.17.2[FS] |  | 19Workday | 21FS | 0% |  | £E. 0 | 152 Hour | £E.0 | 2026-02-27 | 2026-03-26 | 2026-08-01 | 2026-07-31 | 110.1 Workday |  |  |  |  | £E. |  |  | The task of 3 | 91.1 Workday |  | Not Started | None | 이영진
4 | 1.1.2 | Stage 2. FPH detector 모델 검증 | 2026-06-01 | 5FS; 6FS; 7FS; 8FS; 9FS; 10FS | 2026-06-30 | 1.1.17.2[FS] | 1.1.3[FS]; 1.1.4[FS]; 1.1.5[FS]; 1.1.6[FS]; 1.1.7[FS]; 1.1.8[FS] | 22Workday | 21FS | 0% |  | £E. 0 | 176 Hour | £E.0 | 2026-06-01 | 2026-06-30 | 2026-08-01 | 2026-07-31 | 45 Workday |  |  |  |  | £E. |  |  | The task of 3 | 23 Workday |  | Not Started | None | 이영진
5 | 1.1.3 | Stage 1. Face landmark estimator 모델 검증 | 2026-03-02 |  | 2026-03-31 | 1.1.2[FS] |  | 22Workday | 4FS | 0% |  | £E. 0 | 0 Hour | £E.0 | 2026-03-02 | 2026-03-31 | 2026-08-01 | 2026-07-31 | 88 Workday |  |  |  |  | £E.0 |  |  | The task of 3 | 66 Workday |  | Not Started | None | 최호승
6 | 1.1.4 | Stage 2. Face landmark estimator 모델 검증 | 2026-03-02 |  | 2026-03-31 | 1.1.2[FS] |  | 22Workday | 4FS | 0% |  | £E. 0 | 168 Hour | £E.0 | 2026-03-02 | 2026-03-31 | 2026-08-01 | 2026-07-31 | 23 Workday |  |  |  |  | £E. |  |  | The task of 3 | 2 Workday |  | Not Started | None | 최호승
7 | 1.1.5 | Stage 1. Head pose estimator 모델 검증 | 2026-04-01 |  | 2026-04-30 | 1.1.2[FS] |  | 22Workday | 4FS | 0% |  | £E. 0 | 176 Hour | £E.0 | 2026-04-01 | 2026-04-30 | 2026-08-01 | 2026-07-31 | 23 Workday |  |  |  |  | £E. |  |  | The task of 3 | 1 Workday |  | Not Started | None | 최호승
8 | 1.1.6 | Stage 2. Head pose estimator 모델 검증 | 2026-07-01 |  | 2026-07-30 | 1.1.2[FS] |  | 22Workday | 4FS | 0% |  | £E. 0 | 176 Hour | £E.0 | 2026-07-01 | 2026-07-30 | 2026-08-01 | 2026-07-31 | 23 Workday |  |  |  |  | £E. |  |  | The task of 3 | 1 Workday |  | Not Started | None | 최호승
9 | 1.1.7 | Stage 1. Gaze estimator 모델 검증 | 2026-05-01 |  | 2026-05-28 | 1.1.2[FS] |  | 20Workday | 4FS | 0% |  | £E. 0 | 40 Hour | £E.0 | 2026-05-01 | 2026-05-28 | 2026-08-01 | 2026-07-31 | 23 Workday |  |  |  |  | £E. |  |  | The task of 3 | 18 Workday |  | Not Started | None | 이영진
10 | 1.1.8 | Stage 2. Gaze estimator 모델 검증 | 2026-07-02 |  | 2026-07-31 | 1.1.2[FS] |  | 22Workday | 4FS | 0% |  | £E. 0 | 176 Hour | £E.0 | 2026-07-02 | 2026-07-31 | 2026-07-02 | 2026-07-31 | 0 Workday | Yes |  |  |  | £E. |  |  | The task of 3 | 0 Workday |  | Not Started | None | 이영진
11 | 1.1.9 | Stage 1. 2D body keypoint estimator 모델 검증 | 2026-02-27 |  | 2026-03-31 | 1.1.17.2[FS] |  | 22Workday | 21FS | 0% |  | £E. 0 | 176 Hour | £E.0 | 2026-02-27 | 2026-03-31 | 2026-08-01 | 2026-07-31 | 110.1 Workday |  |  |  |  | £E. |  |  | The task of 3 | 88.1 Workday |  | Not Started | None | 이재희
12 | 1.1.10 | Stage 2. 2D body keypoint estimator 모델 검증 | 2026-06-01 | 13FS; 14FS | 2026-06-30 | 1.1.17.2[FS] | 1.1.11[FS]; 1.1.12[FS] | 22Workday | 21FS | 0% |  | £E. 0 | 176 Hour | £E.0 | 2026-06-01 | 2026-06-30 | 2026-08-01 | 2026-07-31 | 45 Workday |  |  |  |  | £E. |  |  | The task of 3 | 23 Workday |  | Not Started | None | 이재희
13 | 1.1.11 | Stage 1. 3D body keypoint estimator 모델 검증 | 2026-05-01 |  | 2026-05-28 | 1.1.10[FS] |  | 20Workday | 12FS | 0% |  | £E. 0 | 160 Hour | £E.0 | 2026-05-01 | 2026-05-28 | 2026-08-01 | 2026-07-31 | 23 Workday |  |  |  |  | £E.0 |  |  | The task of 3 | 3 Workday |  | Not Started | None | 이재희
14 | 1.1.12 | Stage 2. 3D body keypoint estimator 모델 검증 | 2026-07-01 |  | 2026-07-31 | 1.1.10[FS] |  | 23Workday | 12FS | 0% |  | £E. 0 | 184 Hour | £E.0 | 2026-07-01 | 2026-07-31 | 2026-07-01 | 2026-07-31 | 0 Workday | Yes |  |  |  | £E.0 |  |  | The task of 3 | 0 Workday |  | Not Started | None | 이재희
15 | 1.1.13 | Stage 1. Behavior Classifier 모델 검증 | 2026-02-27 |  | 2026-03-27 | 1.1.17.2[FS] |  | 20Workday | 21FS | 0% |  | £E. 0 | 160 Hour | £E.0 | 2026-02-27 | 2026-03-27 | 2026-08-01 | 2026-07-31 | 110.1 Workday |  |  |  |  | £E. |  |  | The task of 3 | 90.1 Workday |  | Not Started | None | 이영진
16 | 1.1.14 | Stage 2. Behavior Classifier 모델 검증 | 2026-04-01 |  | 2026-04-27 | 1.1.17.2[FS] |  | 19Workday | 21FS | 0% |  | £E. 0 | 152 Hour | £E.0 | 2026-04-01 | 2026-04-27 | 2026-08-01 | 2026-07-31 | 88 Workday |  |  |  |  | £E. |  |  | The task of 3 | 69 Workday |  | Not Started | None | 이영진
17 | 1.1.15 | Stage 1. Seatbelt Classifier 모델 검증 | 2026-02-27 |  | 2026-03-31 | 1.1.17.2[FS] |  | 22Workday | 21FS | 0% |  | £E. 0 | 176 Hour | £E.0 | 2026-02-27 | 2026-03-31 | 2026-08-01 | 2026-07-31 | 110.1 Workday |  |  |  |  | £E. |  |  | The task of 3 | 88.1 Workday |  | Not Started | None | 이영진
18 | 1.1.16 | Stage 2. Seatbelt Classifier 모델 검증 | 2026-06-01 |  | 2026-06-30 | 1.1.17.2[FS] |  | 22Workday | 21FS | 0% |  | £E. 0 | 176 Hour | £E.0 | 2026-06-01 | 2026-06-30 | 2026-08-01 | 2026-07-31 | 45 Workday |  |  |  |  | £E. |  |  | The task of 3 | 23 Workday |  | Not Started | None | 이영진
19 | 1.1.17 | 一、AI Model Embedding | 2026-01-01 |  | 2026-07-31 |  |  | 152Workday |  | 0% |  | £E. 0 | 1,568 Hour | £E.0 | 2026-01-01 | 2026-07-31 | 2026-01-01 | 2026-07-31 | 0 Workday | Yes |  |  |  | £E.0 |  |  | The task of 3 | 0 Workday |  | Not Started | None | 이찬형
20 | 1.1.17.1 | 개발 환경 세팅 | 2026-01-01 | 21FS | 2026-01-30 |  | 1.1.17.2[FS] | 22Workday |  | 0% |  | £E. 0 | 176 Hour | £E.0 | 2026-01-01 | 2026-01-30 | 2026-08-01 | 2026-07-31 | 152 Workday |  |  |  |  | £E. |  |  | The task of 4 | 130 Workday |  | Not Started | None | 이찬형
21 | 1.1.17.2 | 하드웨어 인터페이싱 | 2026-02-02 | 3FS; 4FS; 11FS; 12FS; 15FS; 16FS; 17FS; 18FS; 22FS; 23FS | 2026-02-27 | 1.1.17.1[FS] | 1.1.1[FS]; 1.1.2[FS]; 1.1.9[FS]; 1.1.10[FS]; 1.1.13[FS]; 1.1.14[FS]; 1.1.15[FS]; 1.1.16[FS]; 1.1.17.3[FS]; 1.1.17.4[FS] | 20Workday | 20FS | 0% |  | £E. 0 | 160 Hour | £E.0 | 2026-02-02 | 2026-02-27 | 2026-08-01 | 2026-07-31 | 130 Workday |  |  |  |  | £E. |  |  | The task of 4 | 110 Workday |  | Not Started | None | 이찬형
22 | 1.1.17.3 | 연산/성능 최적화 | 2026-03-02 |  | 2026-07-31 | 1.1.17.2[FS] |  | 110Workday | 21FS | 0% |  | £E. 0 | 880 Hour | £E.0 | 2026-03-02 | 2026-07-31 | 2026-03-02 | 2026-07-31 | 0 Workday | Yes |  |  |  | £E. |  |  | The task of 4 | 0 Workday |  | Not Started | None | 이찬형
23 | 1.1.17.4 | 이미지 라이브러리 적용 | 2026-03-02 | 24FS | 2026-03-31 | 1.1.17.2[FS] | 1.1.17.5[FS] | 22Workday | 21FS | 0% |  | £E. 0 | 176 Hour | £E.0 | 2026-03-02 | 2026-03-31 | 2026-08-01 | 2026-07-31 | 110 Workday |  |  |  |  | £E. |  |  | The task of 4 | 88 Workday |  | Not Started | None | 이찬형
24 | 1.1.17.5 | 모델 후처리 최신화 | 2026-04-01 |  | 2026-04-30 | 1.1.17.4[FS] |  | 22Workday | 23FS | 0% |  | £E. 0 | 176 Hour | £E.0 | 2026-04-01 | 2026-04-30 | 2026-08-01 | 2026-07-31 | 88 Workday |  |  |  |  | £E. |  |  | The task of 4 | 66 Workday |  | Not Started | None | 이찬형

## Resource
ID | Name | Max Units | Type | Standard Rate | Overtime Rate | Cost Per | Group | E-Mail | Notes | OverWork
8 | 이영진 | 100% | People | £E.0Hour | £E.0Hour | £E.0 | SW Part
9 | 최호승 | 100% | People | £E.0Hour | £E.0Hour | £E.0 | AI Part
10 | 이재희 | 100% | People | £E.0Hour | £E.0Hour | £E.0 | AI Part
11 | 이찬형 | 100% | People | £E.0Hour | £E.0Hour | £E.0 | SW Part

## Assignments
Task | Resource | Progress | Work | Unit
Phase One - Software Deployment | 이영진 | 0% | 152 Hour | 100%
Phase One - Software Deployment | 최호승 | 0% | 176 Hour | 100%
Phase One - Software Deployment | 이재희 | 0% | 176 Hour | 100%
Phase One - Software Deployment | 이찬형 | 0% | 176 Hour | 100%
一、AI Model deployment | 이영진 | 0% | 152 Hour | 100%
一、AI Model deployment | 최호승 | 0% | 176 Hour | 100%
一、AI Model deployment | 이재희 | 0% | 176 Hour | 100%
一、AI Model deployment | 이찬형 | 0% | 176 Hour | 100%
Stage 1. FPH detector 모델 검증 | 이영진 | 0% | 152 Hour | 100%
Stage 2. FPH detector 모델 검증 | 이영진 | 0% | 176 Hour | 100%
Stage 1. Face landmark estimator 모델 검증 | 최호승 | 0% | 176 Hour | 100%
Stage 2. Face landmark estimator 모델 검증 | 최호승 | 0% | 168 Hour | 100%
Stage 1. Head pose estimator 모델 검증 | 최호승 | 0% | 176 Hour | 100%
Stage 2. Head pose estimator 모델 검증 | 최호승 | 0% | 176 Hour | 100%
Stage 1. Gaze estimator 모델 검증 | 이영진 | 0% | 40 Hour | 100%
Stage 2. Gaze estimator 모델 검증 | 이영진 | 0% | 176 Hour | 100%
Stage 1. 2D body keypoint estimator 모델 검증 | 이재희 | 0% | 176 Hour | 100%
Stage 2. 2D body keypoint estimator 모델 검증 | 이재희 | 0% | 176 Hour | 100%
Stage 1. 3D body keypoint estimator 모델 검증 | 이재희 | 0% | 160 Hour | 100%
Stage 2. 3D body keypoint estimator 모델 검증 | 이재희 | 0% | 184 Hour | 100%
Stage 1. Behavior Classifier 모델 검증 | 이영진 | 0% | 160 Hour | 100%
Stage 2. Behavior Classifier 모델 검증 | 이영진 | 0% | 152 Hour | 100%
Stage 1. Seatbelt Classifier 모델 검증 | 이영진 | 0% | 176 Hour | 100%
Stage 2. Seatbelt Classifier 모델 검증 | 이영진 | 0% | 176 Hour | 100%
一、AI Model Embedding | 이찬형 | 0% | 176 Hour | 100%
개발 환경 세팅 | 이찬형 | 0% | 176 Hour | 100%
하드웨어 인터페이싱 | 이찬형 | 0% | 160 Hour | 100%
연산/성능 최적화 | 이찬형 | 0% | 880 Hour | 100%
이미지 라이브러리 적용 | 이찬형 | 0% | 176 Hour | 100%
모델 후처리 최신화 | 이찬형 | 0% | 176 Hour | 100%